## Sheet1
Gantt Chart
|  | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13-17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25
|  | 2018-10-25 | 2018-11-01 | 2018-11-08 | 2018-11-15 | 2018-11-22 | 2018-11-29 | 2018-12-06 | 2018-12-13 | 2018-12-20 | 2018-01-24 | 2018-01-31 | 2018-02-07 | 2018-02-14 | 2018-02-21 | 2018-02-28 | 2018-03-07 | 2018-03-14 | 2018-03-21 | 2018-03-28 | 2018-04-04 | 2018-04-11
Literature Review
1 | Research articles to gain information
2 | Understand previous uses of scraped data in similar projects
3 | Review the terms and conditions of the company used
4 | Literature reviews of articles found | bar: Week 18 to Week 20
Methodology
5 | Develop File Input | bar: Week 18; Week 20
6 | Project Management writeup | bar: Week 18 to Week 20
7 | Software Development writeup | bar: Week 18 to Week 20
8 | Toolset and Machine Environment writeup | bar: Week 19 to Week 20
9 | Research Methods writeup
Design, Development and Evaluation
10 | Design a report to show recorded data
11 | Software Development writeup | bar: Week 21 to Week 23
12 | Research Projects writup | bar: Week 21 to Week 21
13 | Conclude and evaluate | bar: Week 21 to Week 24
14 | bar: Week 21 to Week 21
15 | bar: Week 21 to Week 24